## Gantt Chart
Schedule

PROJECT TITLE		Material Breeding Simulator 2020				COMPANY NAME					Solid Metal Kite
PROJECT MANAGER		Sam Kagan				DATE					4/3/20

WBS NUMBER	TASK TITLE	START DATE	DUE DATE	DURATION	PCT OF TASK COMPLETE	PHASE ONE					PHASE TWO					PHASE THREE					PHASE FOUR					PHASE FOUR
					WEEK 1					WEEK 2					WEEK 4					WEEK 5					WEEK 7					WEEK 8					WEEK 10					WEEK 11					WEEK 10					WEEK 11
					M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F	M	T	W	R	F
1	Learn Godot and Create Project
1.1	Do Godot 2D tutorial	3/9/20	3/13/20	4	100%
1.2	Do Godot 3D tutorial	3/30/20	4/3/20	4	0%
1.3	Create new project	3/17/20	3/17/20	1	0%
1.4	Make project a git repo	3/17/20	3/17/20	1	0%
1.5	Push repo to GitHub	3/17/20	3/17/20	1	0%
2	Design Game
2.1	Write up pitch	3/5/18	3/6/18	1	100%
2.2	Draft design document	3/6/18	3/9/18	3	100%
2.3	Define material sexual reproduction	4/1/20	4/8/20	7	0%
2.3.1	Define reproduction algorithm	4/1/20	4/6/20	4	0%
2.3.2	Define initial genome	4/6/20	4/8/20	2	50%
3	Project Conception and Initiation
3.1	Status and Tracking			0	0%
3.2	KPIs			0	0%
3.2.1	Monitoring			0	0%
3.2.2	Forecasts			0	0%
3.3	Project Updates			0	0%
3.3.1	Chart Updates			0	0%
4	Project Performance / Monitoring
4.1	Project Objectives			0	0%
4.2	Quality Deliverables			0	0%
4.3	Effort and Cost Tracking			0	0%
4.4	Project Performance			0	0%